## Sheet1
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Create a pre-loading plan | Write down each and every step of the operation | Before the bunkering operation | Must be comprehensive and detailed | Example bunkering checklist | Personnel involved in operation must be familiarized with preloading plan and well trained | Training exercises and emergency response drills | Ineffective bunkering checklist
| Define personnel that will take part in operation |  | Give each member specific tasks | Duty assignment table |  |  | Overworked personnel
Personnel shouldn’t work more than 14h in a 24h period
| Determine the level and type of liquid in all bunker tanks |  | Be thorough with sounding procedure | Tank tables, sounding tape, oil record book |  | Tank sounding | Error in selection of appropriate tanks
| Determine which bunker tanks should be filled |  | Avoid mixing different batches of fuel oil | Compatibility test, if necessary. |  | - | Incompatibility of different batches
If mixing is unavoidable, minimize ratio of residual oil in each bunker tank
| Determine the capacity of bunker tanks to be filled |  | Calculate the final ullage or innage of each bunker tank | Tank tables |  | - | Capacity miscalculation
|  |  | If necessary, perform tank to tank transfer of residual oils | Oil transfer pumps
| Determine the bunker tanks’ filling sequence |  | Beware of impact in vessel's stability | Water ballast tanks |  | - | Excessive trim / heel /list
| Designate an overflow tank to transfer excess fuel if the need arises |  | Ensure that overflow tank remains empty for emergency use | Overflow tank |  | - | Overflow tank rendered useless
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Put in place firefighting measures | Rig fire wires fore and aft (if applicable) | Before the bunkering operation | Must be capable of towing the ship | Fire wires, tow boat | Responsible personnel | - | Fire wire breaks during towing
| Post no smoking notice near the bunkering station |  | Must be strictly enforced and designated smoking areas should be established | - |  | - | Source of open flame
| Post no hot work notice near the bunkering station |  | Must be strictly enforced | - |  | -
| Ground the main radio transmitter aerials |  | - | Main radio transmitter |  | - | Possible creation of spark
| Switch off radar |  | - | Radar |  | -
| Switch VHF/UHF transceivers and AIS equipment on the correct power mode or off. |  | - | VHF/UHF transceivers, AIS equipment |  | -
| Prepare fire hoses and fire-fighting equipment for immediate use |  | Must be in proper working condition | Fire fighting equipment |  | - | Inability to combat fire
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Put in place measures against oil spills | Place oil spill clean up gear adjacent to bunkering station | Before the bunkering operation | Must be in accordance with SOPEP | Sawdust, rugs, oil absorbents, dispersants, PPE, waste containers | Responsible personnel | - | Clean up efforts rendered inefficient
| Fit save-alls with drain plugs |  | Must be effectively sealed | Drain plugs |  | - | Spilled oil escapes from containment and causes water pollution
Ensure that no non-bunkering related leaks could fill the containment arrangements
| Plug deck scuppers and freeing ports |  | Must be effectively sealed |  |  | -
Ensure that no non-bunkering related leaks could fill the containment arrangements
| Have oil booms ready to launch, if available | Before oil spreads extensively | Better to be deployed as a preacaution | Oil booms | Emergency response personnel | -
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Perform the berthing operation of the vessel | Check that water around vessel is oil free | Prior to mooring | - | - | Responsible personnel | Visual check | Oil pollution goes unnoticed
| Ensure there is no danger of collision |  | Watch out for protruding objects | - |  |  | Collision, damage to vessel
|  |  | Confirm that fenders are in good condition | Fenders
| Safely moor the vessel with the supplier | - | Mooring lines must be in good condition | Mooring lines | Appoint watchman to tend mooring lines during bunkering | - | Failure of mooring lines
|  |  | Mooring lines must be fastened to appropriate sections of the vessel |  |  |  | Damage to vessel
|  |  | Enough mooring lines should be fastened |  |  |  | Failure of mooring lines
| If possible, lay out an oil fence around vessel and supplier | After mooring | Oil fence should surround the vessel and the supplier | Oil fence | Vessel or supplier | - | Oil pollution further exacerbated
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Attach bunkering hose to manifold | Ensure that the bunkering hose has enough length | Prior to attaching bunkering hose | - | - | Vessel's representative on supplier's facility | - | Hose damaged or disconnected during vessel's pitching / rolling
| Ensure that the bunkering hose’s weight does not exceed the SWL of the vessel’s lifting gear |  | - | - |  | - | Lifting gear failure
| Attach the bunkering hose | - | Make sure the connections are securely bolted | Crane, bunkering hose, torque wrench, bolts | Place watchman to manifold | Manual check | Hose disconnection
| Ensure that the hose is properly supported | After attaching bunkering hose | Hose must be supported appropriately to prevent kinking, bending, excessive stress | Hose floats, hose supports |  |  | Hose damaged, submerged
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Start pumping at minimum rate | Open manifold valve | After bunkering hose securely connected | Manifold valve must be fully open | Manifold valve | Responsible personnel | Manual check, readings of attached gauges | Increase in pressure inside bunkering hose
| Inform the supplier to start pumping at minimum rate | After opening manifold valve | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Misunderstanding in pumping rate could create overpressure
| Check for leakages. | While pumping at minimum rate | Even minor leaks can contribute to pollution if ignored | Drip trays, save-alls | All watchmen | Visual confirmation | Pipeline leakage
| Check that bunker is routed to the intended bunker tank(s) only. | Regularly | Check that valves are operational, do not assume wrong tanks are not being filled | Pipeline and tank valves | Responsible personnel | Routine sounding of all tanks | Filling of the wrong tank
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Perform change-over of bunker tanks being filled | Inform the supplier to slow down the rate of incoming bunkers. | Once tank level is close to safety limit | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Tank overflow
| Partially open the valve(s) to the next bunker tank(s) |  | Check that valves are operational, do not assume they are working properly | Pipeline and tank valves, tank tables, sounding tape | Responsible personnel | Sounding of newly opened tank(s)
| Confirm that air is flowing out of the next bunker tank’s air vent. | Once new tank starts to fill | Do not assume that air vents are functional | Tank air vents | Deck rover watchman | Manual inspection | Tank overpressure
| Fully open the valve(s) of the next bunker tank(s) to be filled. |  | Check that valves are operational, do not assume they are working properly | Pipeline and tank valves, tank tables, sounding tape | Responsible personnel | Sounding of newly opened tank(s) | Filling of the wrong tank
| Close the valve(s) of the filled bunker tank(s) |  |  |  |  | Sounding of filled bunker tank(s)
| Inform the supplier to gradually increase pumping rate to the one agreed upon. | After filled tank is confirmed closed | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | System overpressure
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Fill the final bunker tank | Inform the supplier that the final bunker tank is reached. | Once final tank is reached | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Miscommunication between parties
| Inform the supplier to reduce pumping rate | Once final bunker tank is close to full | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) / personnel | Regular communication checks
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape |  | Tank sounding
| Inform the supplier to stop pumping | Once final tank reaches safety limit | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) / personnel | Regular communication checks | Tank overflow
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape |  | Tank sounding
| Ensure there is sufficient space in the bunker tank for air blowing | Once pumping has stopped |  | Tank tables, sounding tape | Responsible personnel | Sounding of final bunker tank
| Ensure all sounding pipe caps are closed | Before air blowing | - | Sounding pipe caps |  | Manual inspection | Escape of oil during air blowing
| Inform the supplier to conduct line air blowing using compressed air | After everything else is completed | Final air blowing pressure must be upheld | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | System overpressure

## Sheet2
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Create a pre-loading plan | Write down each and every step of the operation | Before the bunkering operation | Must be comprehensive and detailed | Example bunkering checklist | Personnel involved in operation must be familiarized with preloading plan and well trained | Training exercises and emergency response drills | Ineffective bunkering checklist
| Define personnel that will take part in operation |  | Give each member specific tasks | Duty assignment table |  |  | Overworked personnel
Personnel shouldn’t work more than 14h in a 24h period
| Determine the level and type of liquid in all bunker tanks |  | Be thorough with sounding procedure | Tank tables, sounding tape, oil record book |  | Tank sounding | Error in selection of appropriate tanks
| Determine which bunker tanks should be filled |  | Avoid mixing different batches of fuel oil | Compatibility test, if necessary. |  | - | Incompatibility of different batches
If mixing is unavoidable, minimize ratio of residual oil in each bunker tank
| Determine the capacity of bunker tanks to be filled |  | Calculate the final ullage or innage of each bunker tank | Tank tables |  | - | Capacity miscalculation
|  |  | If necessary, perform tank to tank transfer of residual oils | Oil transfer pumps
| Determine the bunker tanks’ filling sequence |  | Beware of impact in vessel's stability | Water ballast tanks |  | - | Excessive trim / heel /list
| Designate an overflow tank to transfer excess fuel if the need arises |  | Ensure that overflow tank remains empty for emergency use | Overflow tank |  | - | Overflow tank rendered useless
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Put in place firefighting measures | Rig fire wires fore and aft (if applicable) | Before the bunkering operation | Must be capable of towing the ship | Fire wires, tow boat | Responsible personnel | - | Fire wire breaks during towing
| Post no smoking notice near the bunkering station |  | Must be strictly enforced and designated smoking areas should be established | - |  | - | Source of open flame
| Post no hot work notice near the bunkering station |  | Must be strictly enforced | - |  | -
| Ground the main radio transmitter aerials |  | - | Main radio transmitter |  | - | Possible creation of spark
| Switch off radar |  | - | Radar |  | -
| Switch VHF/UHF transceivers and AIS equipment on the correct power mode or off. |  | - | VHF/UHF transceivers, AIS equipment |  | -
| Prepare fire hoses and fire-fighting equipment for immediate use |  | Must be in proper working condition | Fire fighting equipment |  | - | Inability to combat fire

## Sheet3
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Put in place measures against oil spills | Place oil spill clean up gear adjacent to bunkering station | Before the bunkering operation | Must be in accordance with SOPEP | Sawdust, rugs, oil absorbents, dispersants, PPE, waste containers | Responsible personnel | - | Clean up efforts rendered inefficient
| Fit save-alls with drain plugs |  | Must be effectively sealed | Drain plugs |  | - | Spilled oil escapes from containment and causes water pollution
Ensure that no non-bunkering related leaks could fill the containment arrangements
| Plug deck scuppers and freeing ports |  | Must be effectively sealed |  |  | -
Ensure that no non-bunkering related leaks could fill the containment arrangements
| Have oil booms ready to launch, if available | Before oil spreads extensively | Better to be deployed as a preacaution | Oil booms | Emergency response personnel | -
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Perform the berthing operation of the vessel | Check that water around vessel is oil free | Prior to mooring | - | - | Responsible personnel | Visual check | Oil pollution goes unnoticed
| Ensure there is no danger of collision |  | Watch out for protruding objects | - |  |  | Collision, damage to vessel
|  |  | Confirm that fenders are in good condition | Fenders
| Safely moor the vessel with the supplier | - | Mooring lines must be in good condition | Mooring lines | Appoint watchman to tend mooring lines during bunkering | - | Failure of mooring lines
|  |  | Mooring lines must be fastened to appropriate sections of the vessel |  |  |  | Damage to vessel
|  |  | Enough mooring lines should be fastened |  |  |  | Failure of mooring lines
| If possible, lay out an oil fence around vessel and supplier | After mooring | Oil fence should surround the vessel and the supplier | Oil fence | Vessel or supplier | - | Oil pollution further exacerbated

## Sheet4
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Attach bunkering hose to manifold | Ensure that the bunkering hose has enough length | Prior to attaching bunkering hose | - | - | Vessel's representative on supplier's facility | - | Hose damaged or disconnected during vessel's pitching / rolling
| Ensure that the bunkering hose’s weight does not exceed the SWL of the vessel’s lifting gear |  | - | - |  | - | Lifting gear failure
| Attach the bunkering hose | - | Make sure the connections are securely bolted | Crane, bunkering hose, torque wrench, bolts | Place watchman to manifold | Manual check | Hose disconnection
| Ensure that the hose is properly supported | After attaching bunkering hose | Hose must be supported appropriately to prevent kinking, bending, excessive stress | Hose floats, hose supports |  |  | Hose damaged, submerged
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Start pumping at minimum rate | Open manifold valve | After bunkering hose securely connected | Manifold valve must be fully open | Manifold valve | Responsible personnel | Manual check, readings of attached gauges | Increase in pressure inside bunkering hose
| Inform the supplier to start pumping at minimum rate | After opening manifold valve | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Misunderstanding in pumping rate could create overpressure
| Check for leakages. | While pumping at minimum rate | Even minor leaks can contribute to pollution if ignored | Drip trays, save-alls | All watchmen | Visual confirmation | Pipeline leakage
| Check that bunker is routed to the intended bunker tank(s) only. | Regularly | Check that valves are operational, do not assume wrong tanks are not being filled | Pipeline and tank valves | Responsible personnel | Routine sounding of all tanks | Filling of the wrong tank
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape

## Sheet5
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Perform change-over of bunker tanks being filled | Inform the supplier to slow down the rate of incoming bunkers. | Once tank level is close to safety limit | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Tank overflow
| Partially open the valve(s) to the next bunker tank(s) |  | Check that valves are operational, do not assume they are working properly | Pipeline and tank valves, tank tables, sounding tape | Responsible personnel | Sounding of newly opened tank(s)
| Confirm that air is flowing out of the next bunker tank’s air vent. | Once new tank starts to fill | Do not assume that air vents are functional | Tank air vents | Deck rover watchman | Manual inspection | Tank overpressure
| Fully open the valve(s) of the next bunker tank(s) to be filled. |  | Check that valves are operational, do not assume they are working properly | Pipeline and tank valves, tank tables, sounding tape | Responsible personnel | Sounding of newly opened tank(s) | Filling of the wrong tank
| Close the valve(s) of the filled bunker tank(s) |  |  |  |  | Sounding of filled bunker tank(s)
| Inform the supplier to gradually increase pumping rate to the one agreed upon. | After filled tank is confirmed closed | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | System overpressure
Task | Critical subtasks | Time | Limitations | Equipment | Personnel | Control Measures | Hazards
Fill the final bunker tank | Inform the supplier that the final bunker tank is reached. | Once final tank is reached | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | Miscommunication between parties
| Inform the supplier to reduce pumping rate | Once final bunker tank is close to full | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) / personnel | Regular communication checks
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape |  | Tank sounding
| Inform the supplier to stop pumping | Once final tank reaches safety limit | Backup communication must be established as a safeguard | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) / personnel | Regular communication checks | Tank overflow
|  |  | Be thorough with sounding procedure | Tank tables, sounding tape |  | Tank sounding
| Ensure there is sufficient space in the bunker tank for air blowing | Once pumping has stopped |  | Tank tables, sounding tape | Responsible personnel | Sounding of final bunker tank
| Ensure all sounding pipe caps are closed | Before air blowing | - | Sounding pipe caps |  | Manual inspection | Escape of oil during air blowing
| Inform the supplier to conduct line air blowing using compressed air | After everything else is completed | Final air blowing pressure must be upheld | Transceivers, visual signals, sound signals, mobile/ satellite phones | Responsible officer(s) | Regular communication checks | System overpressure